## Thesis Project Management
Thesis Project Management | [6 empty] | Powered by
Task ID | Created At | Completed At | Last Modified | Name | Section/Column | Assignee | Assignee Email | Start Date | Due Date | Tags | Notes | Projects | Parent task | Blocked By (Dependencies) | Blocking (Dependencies) | Priority | Phase
1213727762503027 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Schedule regular supervisor meetings | 📋 Planning & Setup | [5 empty] | Set up recurring meetings with your thesis supervisor (recommended: bi-weekly). Add meeting notes and action items as subtasks. | Thesis Project Management |  |  |  | High | Planning
1213727762503026 | 2026-03-18 21:32 |  | 2026-03-18 22:26 | Create detailed thesis timeline | 📋 Planning & Setup |  |  |  | 2026-03-28 |  | Break down the 4-6 month project into phases with specific milestones. Include buffer time for revisions and unexpected delays. | Thesis Project Management |  |  |  | High | Planning
1213727762503025 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Define thesis topic and research questions | 📋 Planning & Setup |  |  |  | 2026-03-25 |  | Finalize your thesis topic, research questions, and objectives with your supervisor. Document the scope and boundaries of your research. | Thesis Project Management |  |  |  | Critical | Planning
1213727762503029 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Finalize research methodology | 🔬 Research & Data Collection |  |  |  | 2026-04-15 |  | Define and document your research methods, data collection procedures, and analysis approach. Get supervisor approval. | Thesis Project Management |  |  |  | Critical | Research
1213727762503028 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Complete literature review | 🔬 Research & Data Collection |  |  |  | 2026-04-30 |  | Conduct comprehensive literature review. Organize sources and identify gaps in existing research that your thesis will address. | Thesis Project Management |  |  |  | Critical | Research
1213727762503031 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Incorporate supervisor feedback | ✍️ Writing & Drafting |  |  |  | 2026-07-01 |  | Review and implement feedback from supervisor on draft chapters. Track changes and maintain version control. | Thesis Project Management |  |  |  | High | Review
1213727762503030 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Complete first draft of all chapters | ✍️ Writing & Drafting |  |  |  | 2026-06-15 |  | Write first drafts of introduction, methodology, results, discussion, and conclusion. Focus on getting ideas down before perfecting. | Thesis Project Management |  |  |  | Critical | Writing
1213727762503034 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Final thesis submission | 🎯 Key Milestones & Deadlines |  |  |  | 2026-07-31 |  | Submit final formatted thesis according to institutional guidelines. Verify all requirements: formatting, binding, digital submission, etc. | Thesis Project Management |  |  |  | Critical | Submission
1213727762503033 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Ethics approval deadline (if applicable) | 🎯 Key Milestones & Deadlines | [5 empty] | Submit ethics application if your research involves human subjects or sensitive data. Allow 4-6 weeks for approval process. | Thesis Project Management |  |  |  | Critical | Planning
1213727762503032 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Submit thesis proposal (if required) | 🎯 Key Milestones & Deadlines | [5 empty] | Prepare and submit formal thesis proposal including research questions, methodology, and timeline. Check institutional requirements. | Thesis Project Management |  |  |  | Critical | Planning
1213727762503036 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Prepare for thesis defense (if required) | 🔍 Review & Finalization | [5 empty] | Create presentation, anticipate questions, and practice your defense. Schedule mock defense with peers or supervisor. | Thesis Project Management |  |  |  | High | Submission
1213727762503035 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Proofread and format thesis | 🔍 Review & Finalization |  |  |  | 2026-07-20 |  | Complete thorough proofreading for grammar, spelling, and formatting. Ensure compliance with institutional style guide and formatting requirements. | Thesis Project Management |  |  |  | High | Review
1213727762503037 | 2026-03-18 21:32 |  | 2026-03-18 21:32 | Organize reference library | 📚 Resources & References | [5 empty] | Set up reference management system (Zotero, Mendeley, EndNote). Maintain organized library of all sources throughout the project. | Thesis Project Management |  |  |  | Medium | Planning